## ورقة1
Type | Current Situation / Considerations | Proposed Solution / Benefits | Feasibility Result
Technical | Manual queue management; long waiting times; overcrowding; no real-time queue tracking. | Web/desktop queue system with database; digital queue numbers; display screen; real-time tracking and notifications. | ✅ Technically feasible
Operational | Manual queue handling is time-consuming; difficulty knowing waiting status; possible resistance to change. | Faster customer service; automated queue handling; estimated waiting time; reduced workload; better customer satisfaction. | ✅ Operationally feasible
Economic | Cost of software, display hardware, setup, training, and maintenance. | Reduces waiting time and administrative workload; improves service capacity; lowers operational costs. | ✅ Cost-effective
Legal | Need to protect customer information and follow applicable data protection requirements. | Use access control, secure storage, backups, and appropriate data privacy/security policies. | ✅ Legally feasible
Schedule | Manual processes delay customer service and management reporting. | Estimated timeline 4 months (requirements → design → development → testing → deployment). | ✅ Achievable timeline

## ورقة2
Cost–Benefit Analysis – Smart Queue Management System |  |  |  |  | Cost–Benefit Analysis – Library Management System
Category | Description | Estimated Cost | Benefits | Estimated Value (per year)
Software | System development and database setup | 70,000 EGP | Automated queue management reduces waiting time, errors, and manual work. | 120,000 EGP savings
Hardware | Display screen, ticket printer, queue terminals, and backup equipment | 45,000 EGP | Faster customer flow and reduced manual queue handling. | 80,000 EGP saved
Training | Employee training and system orientation | 10,000 EGP | Smooth transition and more efficient use of the system. | 25,000 EGP productivity value
Maintenance | Annual software updates, technical support, and hosting | 20,000 EGP | Improves reliability, security, and system availability. | 30,000 EGP saved
Administration | Current manual queue records, paper tickets, and staff time | 15,000 EGP annually | Reduced paperwork and lower administrative workload. | 35,000 EGP saved
User Experience | Customers spend extra time waiting without clear queue information | – | Shorter waiting experience, clearer turn information, and higher satisfaction. | Intangible but high value
Summary
Total Estimated Costs (first year): 160,000 EGP
Total Estimated Annual Benefits/Savings: 290,000 EGP
Payback Period: Within 1 year
Conclusion: The Smart Queue Management System is economically feasible, with clear operational savings and long-term service value.